## Product Backlog
Product Name: | Robot Shop Management System | [9 empty] | Fields in blue expect your input!
Team ID:
Name: | Bora Yang
Initials: | BY
Student ID: | bxy7782
(Additional names for teams only)
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Total Features | Left | Available | Completed | Sprint Ends
Total at Start | 11 | 11 | 1
Sprint 1 | 1 | 10 | 1 | 2017-03-28
Sprint 2 | 2 | 8 | 2 | 2017-04-04
Sprint 3 | 4 | 4 | 3 | 2017-04-11
Sprint 4 | 2 | 2 |  | 2017-04-18
Sprint 5 | 1 | 1 |  | 2017-04-25
Sprint 6 | 1 | 1 |  | 2017-05-02
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
|  |  |  | Sprint # (by team size) | [5 empty] | Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Prio | Status | Actual Sprint # | 1 | 2 | 3 | 4 | Pts | Cml | As a... | I want to... | So that... | Type | Notes
Create_Parts | 1 | CP | 1 | 1 | 1 | 1 | 1 | 21 | 21 | PM | create robot parts | I can define robot models | CLI | No menu required here – run program, create a part
Create_Models | 2 | CP | 2 | 2 | 1 | 1 | 1 | 13 | 34 | PM | define new robot models | RRS can sell them to our Beloved Customers | CLI | Menu needed – create parts, then create a robot model
Browse_Models | 3 | CP | 2 | 2 | 1 | 1 | 1 | 5 | 39 | BC | browse a catalog of robot models | I can buy one or more robots | CLI | Need to list robots models, then list parts in selected model
Create_BC | 4 | CP | 3 | 3 | 2 | 1 | 1 | 3 | 42 | PB | create a new Beloved Customer | I can keep track of who's buying our products | CLI | The usual name, customer number, phone number, and email address
Create_SA | 5 | CP | 3 | 3 | 2 | 1 | 1 | 3 | 45 | PB | create a new Sales Associate | I can keep track of my employees' performance | CLI | Name and employee number at a minimum
Save_Default | 6 | CP | 3 | 3 | 2 | 2 | 1 | 8 | 53 | SA | create a robot order for a Customer | I can sell robots and thus do my job well | CLI | Select robot model and quantity, show details with total price
| 7 | CP | 3 | 3 | 2 | 2 | 2 | 13 | 66 | PB | ensure persistence of the RRS data | we don't lose orders or historical data | CLI | (CLI) Write the data to the default filename and reload it next time the program runs
| 8 | IW |  | 4 | 3 | 2 | 2 | 3 | 69 | All | open a GUI main window | I can interact with RRS Manager with my mouse | GUI | No menu required here – run program, create a part
| 9 | NS |  | 4 | 3 | 2 | 2 | 34 | 103 | PM | create robot parts via GUI dialogs | I can define robot models | GUI | An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
| 10 | NS |  | 5 | 4 | 3 | 3 | 21 | 124 | PM | define new robot models via GUI dialogs | RRS can sell them to our Beloved Customers | GUI | Similar to robot parts (perhaps Create > Robot Model)
| 11 | NS |  | 6 | 4 | 3 | 3 | 8 | 132 | BC | browse a catalog of robots via a GUI report | I can buy one or more robots | GUI | A text output is OK initially, but an attractive HTML-like output is desired (perhaps Report > All Robot Models)
| 12 | NS |  |  | 5 | 4 | 3 | 21 | 153 | SA | create a robot order for a Customer via GUI | I can sell robots and thus do my job well | GUI | As with CLI (and you’ll need the CLI to add BC and SA people)
| 13 | NS |  |  | 5 | 4 | 4 | 13 | 166 | PB | manage a robot order for a Customer via GUI | I can ensure the robot is built and ships | GUI | This will involve a state machine implementation
| 14 | NS |  |  | 5 | 4 | 4 | 8 | 174 | PB | create a new Beloved Customer via GUI | I can keep track of who's buying our products | GUI | The usual name, address, phone number, and email address (perhaps Create > Customer)
| 15 | NS |  |  | 5 | 4 | 4 | 5 | 179 | PB | create a new Sales Associate via GUI | I can keep track of my employees' performance | GUI | Name and employee number at a minimum (perhaps Create > Sales Associate)
| 16 | NS |  |  | 6 | 5 | 4 | 13 | 192 | BC | see pictures of the robots in the GUI catalog | I can see what I'm buying | GUI | Add picture when defining robot model, and show it in the robot model report
| 17 | NS |  |  | 6 | 5 | 4 | 5 | 197 | PB | allow the users to save data explicitly via GUI | we can save data without exiting the program | GUI | Write the data to the default filename on command (perhaps File > Save to the default filename)
| 18 | NS |  |  | 6 | 5 | 4 | 8 | 205 | PB | allow the users to load data explicitly via GUI | we can manage multiple stores in different files | GUI | Read the data from a user-selected file on command (perhaps File > Open)
| 19 | NS |  |  | 6 | 5 | 4 | 8 | 213 | PB | allow the users to save data to a specified name via GUI | we can manage multiple stores in different files | GUI | Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
| 20 | NS |  |  |  | 5 | 5 | 13 | 226 | PB / SA | view a report of orders per SA in the GUI | I can estimate the value of employees / I can justify a raise | GUI | A basic text report is fine (perhaps Report > Orders by Sales Associate)
| 21 | NS |  |  |  | 6 | 5 | 21 | 247 | All | enable basic login by role and customize the GUI | we don't have options that don't apply to our roles | GUI | User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
| 22 | NS |  |  |  | 6 | 5 | 13 | 260 | All | enable copy and paste from text fields | we can save typing | GUI | Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
| 23 | NS |  |  |  | 6 | 6 | 13 | 273 | BC | view my bill (invoice) in the GUI | I can pay for my robots | GUI | A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
| 24 | NS |  |  |  |  | 6 | 8 | 281 | BC | view my orders in the GUI | see what I have coming to me | GUI | A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
| 25 | NS |  |  |  |  | 6 | 8 | 289 | SA | view a sales report in the GUI | I can justify a raise | GUI | A basic text report is fine (perhaps Report > Orders by Sales Associate)
| 26 | NS |  |  |  |  | 6 | 8 | 297 | PB | view a report of all orders in the GUI | I can manage the company | GUI | A basic text report is fine (perhaps Report > All Orders)
| 27 | NS |  |  |  |  | 6 | 13 | 310 | All | Add multi-level undo | Worry less about making mistakes | GUI | This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
| 28 | NS | [5 empty] | 21 | 331 | BC | see a pie chart of a model's component costs | I can decide if I want a different model | GUI | Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
| 29 | NS | [5 empty] | 13 | 344 | SA | create a bulk (2+) order for Customer via GUI | avoid proliferation of orders and paperwork | GUI | Allow more than one robot model (with respective quantity) on a single order
| 30 | NS | [5 empty] | 8 | 352 | PM | hide robot parts via GUI | obsolete parts aren't accidentally used | GUI | Mark robot parts as “obsolete” and don't allow adding them to new robot models
| 31 | NS | [5 empty] | 8 | 360 | PM | hide robot models via GUI | obsolete robots aren't ordered | GUI | Mark robot models as “obsolete” and don't allow adding them to new orders
| 32 | NS | [5 empty] | 21 | 381 | SA | save a draft order and return to it later via GUI | I can multi-task between indecisive customers | GUI | Save an order that hasn't been complete, and allow SA to resume work on it later
Formulas:
Sprint Ends = [Sprint Ends, row above]+7
Note on C34: NS = Not Started IW = In Work IT = In Test CP = Complete

## Sprint 01 Backlog
Sprint # | 1
Start on | 2017-03-24
End on | 2017-03-27
Demo on | 2017-03-27
Total Tasks | 1
Day 7 Left | 1
Day 6 Left | 1
Day 5 Left | 1
Day 4 Left | 1
Day 3 Left | 1
Day 2 Left | 1
Day 1 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
CRP | BY |  | CLI | BY | Create Robot Part | CP | No menu required here – run program, create a part

## Sprint 02 Backlog
Sprint # | 1 | 2
Start on | 2017-03-24 | 2017-03-29
End on | 2017-03-27 | 2017-04-03
Demo on | 2017-03-27 | 2017-04-03
Total Tasks | 1 | 2
Day 7 Left | 1 | 2
Day 6 Left | 1 | 2
Day 5 Left | 1 | 2
Day 4 Left | 1 | 1
Day 3 Left | 1 | 1
Day 2 Left | 1 | 0
Day 1 Left | 0 | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
CRP | BY |  | CLI | BY | Create Robot Part | CP | No menu required here – run program, create a part
DRM | BY |  | CLI | BY | define new robot models | CP | Menu needed – create parts, then create a robot model
BCM | BY |  | CLI | BY | browse a catalog of robot models | CP | Need to list robots models, then list parts in selected model

## Sprint 03 Backlog
Sprint # | 1 | 2 | 3
Start on | 2017-03-24 | 2017-03-29 | 2017-04-05
End on | 2017-03-27 | 2017-04-03 | 2017-04-11
Demo on | 2017-03-27 | 2017-04-03 | 2017-04-11
Total Tasks | 1 | 2 | 4
Day 7 Left | 1 | 2 | 4
Day 6 Left | 1 | 2 | 4
Day 5 Left | 1 | 2 | 3
Day 4 Left | 1 | 1 | 3
Day 3 Left | 1 | 1 | 2
Day 2 Left | 1 | 0 | 2
Day 1 Left | 0 | 0 | 1
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | Create_Parts |  | CLI | BY | Create Robot Part | CP
2 | Create_Models |  | CLI | BY | define new robot models | CP
3 | Browse_Models |  | CLI | BY | browse a catalog of robot models | CP
4 | Create_BC |  | CLI | BY | create a new Beloved Customer | CP
5 | Create_SA |  | CLI | BY | create a new Sales Associate | CP
6 | Create_Order |  | CLI | BY | create a robot order for a Customer | CP
7 | Save_Default |  | CLI | BY | ensure persistence of the RRS data | IW | fail to save and load data